## Retrospective Ideas
Feedback From: | Type: | Description: | Evidence: | Actions:
Customers | Needs improvement | Tablet Navigation | Customer Survey feedback | Project team to work on improving the navigation
Customers | Needs improvement | Technical issues | Customer Survey feedback | IT Team and project team to work on reducing the issues
Customers | Needs improvement | Order accuracy | Customer Survey feedback | Kitchen management to discuss issues
Customers | Went well | Menu implementation | Customer Survey feedback | Enhance menu options
Customers | Went well | Newsletter signup | Customer Survey feedback | Team to work on the content of the newsletter
Customers | Went well | Payment and checkout process | Customer Survey feedback | Management to work on new checkout options like cash payments/ Add cash register at the kitchen for faster checkout
Project team | Went well | Tablet usage | Retrospective | Brainstorm ideas to improve the usage of tablet
Project team | Needs improvement | Table turn time | Retrospective | Reduce waitstaff training time
Project team | Needs improvement | Orders accuracy | Retrospective | Kitchen management to discuss issues
Project team | Went well | Ticket flow | Retrospective | Management to Improve ticket flow
Project team | Went well | POS technical issues | Retrospective | Team to update the solution manual
Project team | Needs improvement | Content update | Retrospective | Development team to work with design team